## Dashboard
Metric | Value
Report Generated On | 07-06-2026
Report Time | 19:46:59
Total Tenders | 200
Under Process | 90
Completed | 100
Cancelled | 10
GM Attention Required | 17
Delayed Ongoing Tenders | 41
Ongoing Before Timeline | 49
Ongoing On Timeline | 0

## GM Attention
Tender ID | Category | Officer ID | Estimate Value (Lakhs) | File/Tender Received Date | Current Stage | Pending With | Planned Date | Delay Days | SLA Status | Tender Status | Remarks
IOC/BD/26-27/002 | SER | O-05 | 14.05 | 2026-01-02 | Tender Floating Date | Rajesh Kumar | 08-01-2026 | 127 | Delayed | Under Process | Tender floated; bids awaited
IOC/BD/26-27/019 | SER | O-05 | 655.16 | 2026-01-15 | TBA Date | Rajesh Kumar | 14-02-2026 | 90 | Delayed | Under Process | Technical evaluation in progress
IOC/BD/26-27/012 | SER | O-10 | 706.72 | 2026-01-09 | PBO Date | Pooja Agarwal | 16-02-2026 | 88 | Delayed | Under Process | File forwarded for PBO approval
IOC/BD/26-27/061 | MAT | O-02 | 15.77 | 2026-02-15 | NIT Date | Neha Gupta | 18-02-2026 | 86 | Delayed | Under Process | NIT draft under preparation
IOC/BD/26-27/033 | SER | O-05 | 65.99 | 2026-01-25 | TBA Date | Rajesh Kumar | 24-02-2026 | 80 | Delayed | Under Process | Technical evaluation in progress
IOC/BD/26-27/040 | WRK | O-04 | 16.3 | 2026-01-30 | TBA Date | Amit Singh | 01-03-2026 | 75 | Delayed | Under Process | Technical evaluation in progress
IOC/BD/26-27/027 | MAT | O-01 | 92.89 | 2026-01-21 | Workability/Reasonability Date | Sunil Mehta | 04-03-2026 | 72 | Delayed | Under Process | Price reasonability/workability under review
IOC/BD/26-27/059 | SER | O-09 | 775.93 | 2026-02-14 | Technical Bid Opening Date | Arjun Yadav | 09-03-2026 | 67 | Delayed | Under Process | Technical bid opening due
IOC/BD/26-27/046 | MAT | O-01 | 678.51 | 2026-02-04 | CBA Date | Priya Sharma | 11-03-2026 | 65 | Delayed | Under Process | Commercial evaluation in progress
IOC/BD/26-27/090 | SER | O-06 | 10.48 | 2026-03-09 | Tender Floating Date | Vikas Sharma | 15-03-2026 | 61 | Delayed | Under Process | Tender floated; bids awaited
IOC/BD/26-27/048 | SER | O-09 | 53.24 | 2026-02-05 | Price Comparison Date | Arjun Yadav | 16-03-2026 | 60 | Delayed | Under Process | Price comparison statement under preparation
IOC/BD/26-27/044 | MAT | O-03 | 85.51 | 2026-02-02 | Award Approval Date | Sunil Mehta & Rakesh Srivastava | 24-03-2026 | 52 | Delayed | Under Process | Award approval under process
IOC/BD/26-27/104 | WRK | O-04 | 9463.54 | 2026-03-20 | Workability/Reasonability Date | Sunil Mehta | 01-05-2026 | 14 | Delayed | Under Process | Award approval under process
IOC/BD/26-27/097 | SER | O-09 | 418.51 | 2026-03-14 | Award Approval Date | Sunil Mehta & Rakesh Srivastava | 03-05-2026 | 12 | Delayed | Under Process | Award approval under process
IOC/BD/26-27/170 | SER | O-06 | 5275.13 | 2026-05-08 | Tender Floating Date | Vikas Sharma | 14-05-2026 | 1 | Delayed | Under Process | Tender floated; bids awaited
IOC/BD/26-27/123 | MAT | O-01 | 37.58 | 2026-04-03 | Award Approval Date | Sunil Mehta & Rakesh Srivastava | 23-05-2026 | -8 | Before Timeline | Under Process | Award approval under process
IOC/BD/26-27/137 | MAT | O-03 | 37.82 | 2026-04-14 | Award Approval Date | Sunil Mehta & Rakesh Srivastava | 03-06-2026 | -19 | Before Timeline | Under Process | Award approval under process

## ongoing Tenders
Tender ID | Category | Officer ID | Estimate Value (Lakhs) | File/Tender Received Date | Current Stage | Pending With | Planned Date | Delay Days | SLA Status | Tender Status | Remarks
IOC/BD/26-27/002 | SER | O-05 | 14.05 | 2026-01-02 | Tender Floating Date | Rajesh Kumar | 08-01-2026 | 127 | Delayed | Under Process | Tender floated; bids awaited
IOC/BD/26-27/012 | SER | O-10 | 706.72 | 2026-01-09 | PBO Date | Pooja Agarwal | 16-02-2026 | 88 | Delayed | Under Process | File forwarded for PBO approval
IOC/BD/26-27/019 | SER | O-05 | 655.16 | 2026-01-15 | TBA Date | Rajesh Kumar | 14-02-2026 | 90 | Delayed | Under Process | Technical evaluation in progress
IOC/BD/26-27/027 | MAT | O-01 | 92.89 | 2026-01-21 | Workability/Reasonability Date | Sunil Mehta | 04-03-2026 | 72 | Delayed | Under Process | Price reasonability/workability under review
IOC/BD/26-27/033 | SER | O-05 | 65.99 | 2026-01-25 | TBA Date | Rajesh Kumar | 24-02-2026 | 80 | Delayed | Under Process | Technical evaluation in progress
IOC/BD/26-27/040 | WRK | O-04 | 16.3 | 2026-01-30 | TBA Date | Amit Singh | 01-03-2026 | 75 | Delayed | Under Process | Technical evaluation in progress
IOC/BD/26-27/044 | MAT | O-03 | 85.51 | 2026-02-02 | Award Approval Date | Sunil Mehta & Rakesh Srivastava | 24-03-2026 | 52 | Delayed | Under Process | Award approval under process
IOC/BD/26-27/046 | MAT | O-01 | 678.51 | 2026-02-04 | CBA Date | Priya Sharma | 11-03-2026 | 65 | Delayed | Under Process | Commercial evaluation in progress
IOC/BD/26-27/048 | SER | O-09 | 53.24 | 2026-02-05 | Price Comparison Date | Arjun Yadav | 16-03-2026 | 60 | Delayed | Under Process | Price comparison statement under preparation
IOC/BD/26-27/059 | SER | O-09 | 775.93 | 2026-02-14 | Technical Bid Opening Date | Arjun Yadav | 09-03-2026 | 67 | Delayed | Under Process | Technical bid opening due
IOC/BD/26-27/061 | MAT | O-02 | 15.77 | 2026-02-15 | NIT Date | Neha Gupta | 18-02-2026 | 86 | Delayed | Under Process | NIT draft under preparation
IOC/BD/26-27/090 | SER | O-06 | 10.48 | 2026-03-09 | Tender Floating Date | Vikas Sharma | 15-03-2026 | 61 | Delayed | Under Process | Tender floated; bids awaited
IOC/BD/26-27/092 | MAT | O-03 | 70.22 | 2026-03-11 | PBO Date | Rahul Verma | 18-04-2026 | 27 | Delayed | Under Process | File forwarded for PBO approval
IOC/BD/26-27/095 | SER | O-09 | 304.96 | 2026-03-13 | Workability/Reasonability Date | Sunil Mehta | 24-04-2026 | 21 | Delayed | Under Process | Award approval under process
IOC/BD/26-27/096 | MAT | O-02 | 78.37 | 2026-03-14 | Workability/Reasonability Date | Sunil Mehta | 25-04-2026 | 20 | Delayed | Under Process | Negotiation in progress; revised offer awaited
IOC/BD/26-27/097 | SER | O-09 | 418.51 | 2026-03-14 | Award Approval Date | Sunil Mehta & Rakesh Srivastava | 03-05-2026 | 12 | Delayed | Under Process | Award approval under process
IOC/BD/26-27/098 | WRK | O-04 | 32.12 | 2026-03-15 | Negotiation Date | Amit Singh | 01-05-2026 | 14 | Delayed | Under Process | Negotiation in progress; revised offer awaited
IOC/BD/26-27/100 | SER | O-06 | 11.25 | 2026-03-17 | Workability/Reasonability Date | Sunil Mehta | 28-04-2026 | 17 | Delayed | Under Process | Price reasonability/workability under review
IOC/BD/26-27/101 | SER | O-06 | 434.26 | 2026-03-17 | Workability/Reasonability Date | Sunil Mehta | 28-04-2026 | 17 | Delayed | Under Process | Price reasonability/workability under review
IOC/BD/26-27/102 | SER | O-06 | 402.46 | 2026-03-18 | Workability/Reasonability Date | Sunil Mehta | 29-04-2026 | 16 | Delayed | Under Process | Price reasonability/workability under review
IOC/BD/26-27/103 | SER | O-10 | 695.56 | 2026-03-19 | Price Comparison Date | Pooja Agarwal | 27-04-2026 | 18 | Delayed | Under Process | Price comparison statement under preparation
IOC/BD/26-27/104 | WRK | O-04 | 9463.54 | 2026-03-20 | Workability/Reasonability Date | Sunil Mehta | 01-05-2026 | 14 | Delayed | Under Process | Award approval under process
IOC/BD/26-27/105 | SER | O-09 | 65.88 | 2026-03-20 | Workability/Reasonability Date | Sunil Mehta | 01-05-2026 | 14 | Delayed | Under Process | Price reasonability/workability under review
IOC/BD/26-27/108 | SER | O-06 | 40.28 | 2026-03-23 | Workability/Reasonability Date | Sunil Mehta | 04-05-2026 | 11 | Delayed | Under Process | Price reasonability/workability under review
IOC/BD/26-27/110 | SER | O-04 | 525.97 | 2026-03-24 | Price Comparison Date | Amit Singh | 02-05-2026 | 13 | Delayed | Under Process | Price comparison statement under preparation
IOC/BD/26-27/117 | SER | O-07 | 638.15 | 2026-03-29 | Order Issued Date | Sandeep Gupta | 19-05-2026 | -4 | Before Timeline | Under Process | Award approved; order issuance pending
IOC/BD/26-27/120 | SER | O-09 | 93.67 | 2026-04-01 | Price Comparison Date | Arjun Yadav | 10-05-2026 | 5 | Delayed | Under Process | Price comparison statement under preparation
IOC/BD/26-27/121 | SER | O-04 | 166.9 | 2026-04-01 | Workability/Reasonability Date | Sunil Mehta | 13-05-2026 | 2 | Delayed | Under Process | Price reasonability/workability under review
IOC/BD/26-27/122 | MAT | O-02 | 94.33 | 2026-04-02 | Workability/Reasonability Date | Sunil Mehta | 14-05-2026 | 1 | Delayed | Under Process | Award approved; order issuance pending
IOC/BD/26-27/123 | MAT | O-01 | 37.58 | 2026-04-03 | Award Approval Date | Sunil Mehta & Rakesh Srivastava | 23-05-2026 | -8 | Before Timeline | Under Process | Award approval under process
IOC/BD/26-27/125 | SER | O-05 | 498.85 | 2026-04-04 | Workability/Reasonability Date | Sunil Mehta | 16-05-2026 | -1 | Before Timeline | Under Process | Award approved; order issuance pending
IOC/BD/26-27/126 | SER | O-04 | 11.45 | 2026-04-05 | Negotiation Date | Amit Singh | 22-05-2026 | -7 | Before Timeline | Under Process | Negotiation in progress; revised offer awaited
IOC/BD/26-27/128 | SER | O-06 | 703.09 | 2026-04-07 | CBA Date | Vikas Sharma | 12-05-2026 | 3 | Delayed | Under Process | Commercial evaluation in progress
IOC/BD/26-27/129 | MAT | O-02 | 205.59 | 2026-04-07 | TBA Date | Neha Gupta | 07-05-2026 | 8 | Delayed | Under Process | Technical evaluation in progress
IOC/BD/26-27/133 | MAT | O-03 | 390.46 | 2026-04-10 | Workability/Reasonability Date | Sunil Mehta | 22-05-2026 | -7 | Before Timeline | Under Process | Award approval under process
IOC/BD/26-27/137 | MAT | O-03 | 37.82 | 2026-04-14 | Award Approval Date | Sunil Mehta & Rakesh Srivastava | 03-06-2026 | -19 | Before Timeline | Under Process | Award approval under process
IOC/BD/26-27/139 | SER | O-07 | 635.98 | 2026-04-15 | Technical Bid Opening Date | Sandeep Gupta | 08-05-2026 | 7 | Delayed | Under Process | Technical bid opening due
IOC/BD/26-27/140 | WRK | O-05 | 51.53 | 2026-04-16 | Order Issued Date | Rajesh Kumar | 06-06-2026 | -22 | Before Timeline | Under Process | Award approved; order issuance pending
IOC/BD/26-27/143 | SER | O-07 | 62.75 | 2026-04-18 | Order Issued Date | Sandeep Gupta | 08-06-2026 | -24 | Before Timeline | Under Process | Award approved; order issuance pending
IOC/BD/26-27/144 | SER | O-10 | 6546.82 | 2026-04-19 | Workability/Reasonability Date | Sunil Mehta | 31-05-2026 | -16 | Before Timeline | Under Process | Award approved; order issuance pending
IOC/BD/26-27/145 | SER | O-09 | 70.41 | 2026-04-20 | CBA Date | Arjun Yadav | 25-05-2026 | -10 | Before Timeline | Under Process | Commercial evaluation in progress
IOC/BD/26-27/147 | SER | O-05 | 804.93 | 2026-04-21 | Workability/Reasonability Date | Sunil Mehta | 02-06-2026 | -18 | Before Timeline | Under Process | Award approved; order issuance pending
IOC/BD/26-27/149 | SER | O-09 | 58.77 | 2026-04-23 | Negotiation Date | Arjun Yadav | 09-06-2026 | -25 | Before Timeline | Under Process | Negotiation in progress; revised offer awaited
IOC/BD/26-27/151 | SER | O-07 | 966.76 | 2026-04-24 | Technical Bid Opening Date | Sandeep Gupta | 17-05-2026 | -2 | Before Timeline | Under Process | Technical bid opening due
IOC/BD/26-27/152 | MAT | O-03 | 776.39 | 2026-04-25 | NIT Date | Rahul Verma | 28-04-2026 | 17 | Delayed | Under Process | NIT draft under preparation
IOC/BD/26-27/153 | SER | O-06 | 294.23 | 2026-04-26 | Tender Floating Date | Vikas Sharma | 02-05-2026 | 13 | Delayed | Under Process | Tender floated; bids awaited
IOC/BD/26-27/154 | SER | O-07 | 33.41 | 2026-04-26 | Tender Floating Date | Sandeep Gupta | 02-05-2026 | 13 | Delayed | Under Process | Tender floated; bids awaited
IOC/BD/26-27/155 | SER | O-10 | 700.15 | 2026-04-27 | TBA Date | Pooja Agarwal | 27-05-2026 | -12 | Before Timeline | Under Process | Technical evaluation in progress
IOC/BD/26-27/156 | SER | O-04 | 816.27 | 2026-04-28 | Tender Floating Date | Amit Singh | 04-05-2026 | 11 | Delayed | Under Process | Tender floated; bids awaited
IOC/BD/26-27/157 | SER | O-10 | 475.73 | 2026-04-29 | NIT Date | Pooja Agarwal | 02-05-2026 | 13 | Delayed | Under Process | NIT draft under preparation
IOC/BD/26-27/158 | SER | O-06 | 482.8 | 2026-04-29 | Tender Floating Date | Vikas Sharma | 05-05-2026 | 10 | Delayed | Under Process | Tender floated; bids awaited
IOC/BD/26-27/160 | WRK | O-06 | 336.51 | 2026-05-01 | Tender Floating Date | Vikas Sharma | 07-05-2026 | 8 | Delayed | Under Process | Tender floated; bids awaited
IOC/BD/26-27/161 | SER | O-08 | 23.01 | 2026-05-02 | NIT Date | Manish Verma | 05-05-2026 | 10 | Delayed | Under Process | File received; NIT preparation to be initiated
IOC/BD/26-27/162 | SER | O-06 | 78.84 | 2026-05-02 | NIT Date | Vikas Sharma | 05-05-2026 | 10 | Delayed | Under Process | NIT draft under preparation
IOC/BD/26-27/163 | SER | O-04 | 3353.74 | 2026-05-03 | Technical Bid Opening Date | Amit Singh | 26-05-2026 | -11 | Before Timeline | Under Process | Technical bid opening due
IOC/BD/26-27/164 | MAT | O-01 | 71.32 | 2026-05-04 | TBA Date | Priya Sharma | 03-06-2026 | -19 | Before Timeline | Under Process | Technical evaluation in progress
IOC/BD/26-27/165 | MAT | O-02 | 8570.83 | 2026-05-05 | PBO Date | Neha Gupta | 12-06-2026 | -28 | Before Timeline | Under Process | File forwarded for PBO approval
IOC/BD/26-27/166 | MAT | O-02 | 489.61 | 2026-05-05 | PBO Date | Neha Gupta | 12-06-2026 | -28 | Before Timeline | Under Process | File forwarded for PBO approval
IOC/BD/26-27/167 | MAT | O-02 | 715.66 | 2026-05-06 | PBO Date | Neha Gupta | 13-06-2026 | -29 | Before Timeline | Under Process | File forwarded for PBO approval
IOC/BD/26-27/168 | MAT | O-01 | 1902.3 | 2026-05-07 | TBA Date | Priya Sharma | 06-06-2026 | -22 | Before Timeline | Under Process | Technical evaluation in progress
IOC/BD/26-27/169 | MAT | O-02 | 9638.59 | 2026-05-08 | Technical Bid Opening Date | Neha Gupta | 31-05-2026 | -16 | Before Timeline | Under Process | Technical bid opening due
IOC/BD/26-27/170 | SER | O-06 | 5275.13 | 2026-05-08 | Tender Floating Date | Vikas Sharma | 14-05-2026 | 1 | Delayed | Under Process | Tender floated; bids awaited
IOC/BD/26-27/171 | SER | O-04 | 371.24 | 2026-05-09 | Technical Bid Opening Date | Amit Singh | 01-06-2026 | -17 | Before Timeline | Under Process | Technical bid opening due
IOC/BD/26-27/172 | MAT | O-01 | 4947.94 | 2026-05-10 | Tender Floating Date | Priya Sharma | 16-05-2026 | -1 | Before Timeline | Under Process | Tender floated; bids awaited
IOC/BD/26-27/173 | MAT | O-01 | 79.15 | 2026-05-11 | TBA Date | Priya Sharma | 10-06-2026 | -26 | Before Timeline | Under Process | Technical evaluation in progress
IOC/BD/26-27/174 | SER | O-05 | 560.8 | 2026-05-11 | PBO Date | Rajesh Kumar | 18-06-2026 | -34 | Before Timeline | Under Process | File forwarded for PBO approval
IOC/BD/26-27/175 | SER | O-08 | 586.54 | 2026-05-12 | CBA Date | Manish Verma | 16-06-2026 | -32 | Before Timeline | Under Process | Commercial evaluation in progress
IOC/BD/26-27/176 | SER | O-10 | 3951.16 | 2026-05-13 | CBA Date | Pooja Agarwal | 17-06-2026 | -33 | Before Timeline | Under Process | Commercial evaluation in progress
IOC/BD/26-27/177 | WRK | O-06 | 501.99 | 2026-05-14 | NIT Date | Vikas Sharma | 17-05-2026 | -2 | Before Timeline | Under Process | File received; NIT preparation to be initiated
IOC/BD/26-27/180 | WRK | O-04 | 152.86 | 2026-05-16 | PBO Date | Amit Singh | 23-06-2026 | -39 | Before Timeline | Under Process | File forwarded for PBO approval
IOC/BD/26-27/181 | SER | O-10 | 59.78 | 2026-05-17 | NIT Date | Pooja Agarwal | 20-05-2026 | -5 | Before Timeline | Under Process | NIT draft under preparation
IOC/BD/26-27/182 | SER | O-10 | 157.5 | 2026-05-17 | NIT Date | Pooja Agarwal | 20-05-2026 | -5 | Before Timeline | Under Process | NIT draft under preparation
IOC/BD/26-27/183 | SER | O-10 | 46.2 | 2026-05-18 | TBA Date | Pooja Agarwal | 17-06-2026 | -33 | Before Timeline | Under Process | Technical evaluation in progress
IOC/BD/26-27/184 | SER | O-05 | 4935.39 | 2026-05-19 | NIT Date | Rajesh Kumar | 22-05-2026 | -7 | Before Timeline | Under Process | NIT draft under preparation
IOC/BD/26-27/185 | MAT | O-02 | 80.93 | 2026-05-20 | Tender Floating Date | Neha Gupta | 26-05-2026 | -11 | Before Timeline | Under Process | Tender floated; bids awaited
IOC/BD/26-27/186 | MAT | O-02 | 626.75 | 2026-05-20 | NIT Date | Neha Gupta | 23-05-2026 | -8 | Before Timeline | Under Process | File received; NIT preparation to be initiated
IOC/BD/26-27/187 | SER | O-10 | 639.18 | 2026-05-21 | Technical Bid Opening Date | Pooja Agarwal | 13-06-2026 | -29 | Before Timeline | Under Process | Technical bid opening due
IOC/BD/26-27/188 | SER | O-05 | 6678.39 | 2026-05-22 | NIT Date | Rajesh Kumar | 25-05-2026 | -10 | Before Timeline | Under Process | File received; NIT preparation to be initiated
IOC/BD/26-27/189 | SER | O-05 | 17.8 | 2026-05-23 | NIT Date | Rajesh Kumar | 26-05-2026 | -11 | Before Timeline | Under Process | File received; NIT preparation to be initiated
IOC/BD/26-27/190 | WRK | O-08 | 685.78 | 2026-05-23 | TBA Date | Manish Verma | 22-06-2026 | -38 | Before Timeline | Under Process | Technical evaluation in progress
IOC/BD/26-27/191 | SER | O-07 | 6117.91 | 2026-05-24 | NIT Date | Sandeep Gupta | 27-05-2026 | -12 | Before Timeline | Under Process | NIT draft under preparation
IOC/BD/26-27/192 | SER | O-05 | 178.33 | 2026-05-25 | NIT Date | Rajesh Kumar | 28-05-2026 | -13 | Before Timeline | Under Process | NIT draft under preparation
IOC/BD/26-27/193 | MAT | O-01 | 7409.26 | 2026-05-26 | NIT Date | Priya Sharma | 29-05-2026 | -14 | Before Timeline | Under Process | NIT draft under preparation
IOC/BD/26-27/194 | MAT | O-02 | 417.42 | 2026-05-26 | PBO Date | Neha Gupta | 03-07-2026 | -49 | Before Timeline | Under Process | File forwarded for PBO approval
IOC/BD/26-27/195 | SER | O-10 | 669.3 | 2026-05-27 | Technical Bid Opening Date | Pooja Agarwal | 19-06-2026 | -35 | Before Timeline | Under Process | Technical bid opening due
IOC/BD/26-27/196 | WRK | O-05 | 9641.58 | 2026-05-28 | NIT Date | Rajesh Kumar | 31-05-2026 | -16 | Before Timeline | Under Process | NIT draft under preparation
IOC/BD/26-27/197 | SER | O-10 | 63.6 | 2026-05-29 | Technical Bid Opening Date | Pooja Agarwal | 21-06-2026 | -37 | Before Timeline | Under Process | Technical bid opening due
IOC/BD/26-27/198 | MAT | O-02 | 430.86 | 2026-05-29 | NIT Date | Neha Gupta | 01-06-2026 | -17 | Before Timeline | Under Process | File received; NIT preparation to be initiated
IOC/BD/26-27/199 | WRK | O-04 | 194.72 | 2026-05-30 | CBA Date | Amit Singh | 04-07-2026 | -50 | Before Timeline | Under Process | Commercial evaluation in progress
IOC/BD/26-27/200 | MAT | O-01 | 4419.24 | 2026-05-31 | PBO Date | Priya Sharma | 08-07-2026 | -54 | Before Timeline | Under Process | File forwarded for PBO approval

## Completed Tenders
Tender ID | Category | Officer ID | Estimate Value (Lakhs) | File/Tender Received Date | Current Stage | Pending With | Planned Date | Delay Days | SLA Status | Tender Status | Remarks
IOC/BD/26-27/001 | WRK | O-07 | 2098.14 | 2026-01-01 | Completed | Completed | 2026-03-17 | 24 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/003 | MAT | O-01 | 14.26 | 2026-01-03 | Completed | Completed | 2026-02-27 | 4 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/004 | MAT | O-01 | 86.97 | 2026-01-03 | Completed | Completed | 2026-03-01 | 6 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/005 | MAT | O-03 | 625.35 | 2026-01-04 | Completed | Completed | 2026-04-01 | 36 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/006 | MAT | O-03 | 697.47 | 2026-01-05 | Completed | Completed | 2026-02-21 | -4 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/007 | MAT | O-02 | 14.71 | 2026-01-06 | Completed | Completed | 2026-02-27 | 1 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/008 | MAT | O-02 | 943.99 | 2026-01-06 | Completed | Completed | 2026-04-04 | 37 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/009 | SER | O-09 | 716.91 | 2026-01-07 | Completed | Completed | 2026-03-13 | 14 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/010 | SER | O-08 | 863.78 | 2026-01-08 | Completed | Completed | 2026-03-05 | 5 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/011 | SER | O-04 | 706.02 | 2026-01-09 | Completed | Completed | 2026-03-24 | 23 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/013 | MAT | O-02 | 549.6 | 2026-01-10 | Completed | Completed | 2026-02-25 | -5 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/014 | WRK | O-05 | 431.37 | 2026-01-11 | Completed | Completed | 2026-03-10 | 7 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/015 | SER | O-08 | 3990.98 | 2026-01-12 | Completed | Completed | 2026-03-26 | 22 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/016 | MAT | O-02 | 77.86 | 2026-01-12 | Completed | Completed | 2026-03-09 | 5 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/017 | MAT | O-02 | 1713.92 | 2026-01-13 | Completed | Completed | 2026-04-04 | 30 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/018 | SER | O-10 | 36.15 | 2026-01-14 | Completed | Completed | 2026-03-02 | -4 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/020 | SER | O-09 | 7911.02 | 2026-01-15 | Completed | Completed | 2026-03-07 | 0 | On Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/021 | SER | O-04 | 98.29 | 2026-01-16 | Completed | Completed | 2026-03-08 | 0 | On Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/022 | MAT | O-01 | 640.91 | 2026-01-17 | Completed | Completed | 2026-03-10 | 1 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/023 | SER | O-08 | 664.33 | 2026-01-18 | Completed | Completed | 2026-03-14 | 4 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/024 | MAT | O-02 | 181.47 | 2026-01-18 | Completed | Completed | 2026-03-05 | -5 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/025 | WRK | O-05 | 531.84 | 2026-01-19 | Completed | Completed | 2026-03-07 | -4 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/026 | SER | O-08 | 26.15 | 2026-01-20 | Completed | Completed | 2026-03-16 | 4 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/028 | SER | O-10 | 33.35 | 2026-01-21 | Completed | Completed | 2026-03-16 | 3 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/030 | MAT | O-03 | 167.55 | 2026-01-23 | Completed | Completed | 2026-03-16 | 1 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/031 | MAT | O-02 | 87.24 | 2026-01-24 | Completed | Completed | 2026-04-22 | 37 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/034 | WRK | O-04 | 523.4 | 2026-01-26 | Completed | Completed | 2026-04-09 | 22 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/035 | MAT | O-03 | 863.14 | 2026-01-27 | Completed | Completed | 2026-03-27 | 8 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/036 | SER | O-07 | 432.19 | 2026-01-27 | Completed | Completed | 2026-04-10 | 22 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/037 | WRK | O-07 | 68.55 | 2026-01-28 | Completed | Completed | 2026-03-17 | -3 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/038 | SER | O-05 | 54.85 | 2026-01-29 | Completed | Completed | 2026-03-25 | 4 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/039 | SER | O-07 | 512.28 | 2026-01-30 | Completed | Completed | 2026-04-17 | 26 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/041 | SER | O-07 | 7676.96 | 2026-01-31 | Completed | Completed | 2026-03-20 | -3 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/042 | SER | O-06 | 88.36 | 2026-02-01 | Completed | Completed | 2026-03-30 | 6 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/043 | SER | O-04 | 568.09 | 2026-02-02 | Completed | Completed | 2026-04-17 | 23 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/045 | WRK | O-05 | 18.1 | 2026-02-03 | Completed | Completed | 2026-04-03 | 8 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/047 | MAT | O-03 | 88.77 | 2026-02-05 | Completed | Completed | 2026-04-30 | 33 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/049 | SER | O-04 | 854.73 | 2026-02-06 | Completed | Completed | 2026-03-30 | 1 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/050 | SER | O-09 | 293.79 | 2026-02-07 | Completed | Completed | 2026-04-11 | 12 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/051 | SER | O-08 | 655.5 | 2026-02-08 | Completed | Completed | 2026-04-08 | 8 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/052 | MAT | O-01 | 7002.32 | 2026-02-08 | Completed | Completed | 2026-04-05 | 5 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/053 | SER | O-08 | 538.08 | 2026-02-09 | Completed | Completed | 2026-04-08 | 7 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/055 | SER | O-04 | 905.81 | 2026-02-11 | Completed | Completed | 2026-05-09 | 36 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/056 | SER | O-10 | 7354.6 | 2026-02-11 | Completed | Completed | 2026-04-01 | -2 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/057 | SER | O-04 | 778.96 | 2026-02-12 | Completed | Completed | 2026-04-30 | 26 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/058 | WRK | O-09 | 9623.26 | 2026-02-13 | Completed | Completed | 2026-04-09 | 4 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/062 | SER | O-05 | 176.73 | 2026-02-16 | Completed | Completed | 2026-04-16 | 8 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/063 | SER | O-08 | 941.03 | 2026-02-17 | Completed | Completed | 2026-04-08 | -1 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/064 | SER | O-04 | 594.95 | 2026-02-17 | Completed | Completed | 2026-04-13 | 4 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/065 | MAT | O-02 | 652.33 | 2026-02-18 | Completed | Completed | 2026-04-05 | -5 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/066 | SER | O-10 | 96.34 | 2026-02-19 | Completed | Completed | 2026-04-13 | 2 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/067 | SER | O-08 | 3150 | 2026-02-20 | Completed | Completed | 2026-04-08 | -4 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/068 | SER | O-08 | 225.65 | 2026-02-21 | Completed | Completed | 2026-04-07 | -6 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/069 | SER | O-08 | 15.89 | 2026-02-21 | Completed | Completed | 2026-04-26 | 13 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/070 | SER | O-07 | 53.72 | 2026-02-22 | Completed | Completed | 2026-04-16 | 2 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/071 | SER | O-05 | 434.99 | 2026-02-23 | Completed | Completed | 2026-04-14 | -1 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/072 | SER | O-05 | 172.59 | 2026-02-24 | Completed | Completed | 2026-04-14 | -2 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/073 | SER | O-08 | 56.49 | 2026-02-24 | Completed | Completed | 2026-04-14 | -2 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/074 | MAT | O-01 | 5830.49 | 2026-02-25 | Completed | Completed | 2026-05-11 | 24 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/075 | SER | O-06 | 684.38 | 2026-02-26 | Completed | Completed | 2026-05-16 | 28 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/076 | SER | O-04 | 80.31 | 2026-02-27 | Completed | Completed | 2026-05-18 | 29 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/077 | SER | O-04 | 666.13 | 2026-02-27 | Completed | Completed | 2026-05-06 | 17 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/078 | SER | O-10 | 92.95 | 2026-02-28 | Completed | Completed | 2026-05-17 | 27 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/079 | SER | O-10 | 858.76 | 2026-03-01 | Completed | Completed | 2026-04-26 | 5 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/080 | SER | O-10 | 578.7 | 2026-03-02 | Completed | Completed | 2026-04-27 | 5 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/081 | MAT | O-03 | 670.67 | 2026-03-02 | Completed | Completed | 2026-04-20 | -2 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/082 | MAT | O-03 | 6927.75 | 2026-03-03 | Completed | Completed | 2026-05-24 | 31 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/083 | SER | O-10 | 2427 | 2026-03-04 | Completed | Completed | 2026-05-25 | 31 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/084 | SER | O-06 | 3453.12 | 2026-03-05 | Completed | Completed | 2026-04-24 | -1 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/085 | SER | O-09 | 3953.43 | 2026-03-05 | Completed | Completed | 2026-05-09 | 14 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/086 | SER | O-09 | 72.89 | 2026-03-06 | Completed | Completed | 2026-04-26 | 0 | On Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/087 | SER | O-06 | 537.45 | 2026-03-07 | Completed | Completed | 2026-05-25 | 28 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/088 | MAT | O-03 | 902.64 | 2026-03-08 | Completed | Completed | 2026-04-30 | 2 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/089 | SER | O-09 | 2316.87 | 2026-03-08 | Completed | Completed | 2026-05-03 | 5 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/093 | MAT | O-03 | 355.87 | 2026-03-11 | Completed | Completed | 2026-06-06 | 36 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/094 | MAT | O-03 | 78.59 | 2026-03-12 | Completed | Completed | 2026-05-03 | 1 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/099 | SER | O-04 | 703.23 | 2026-03-16 | Completed | Completed | 2026-05-13 | 7 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/107 | MAT | O-01 | 53.38 | 2026-03-22 | Completed | Completed | 2026-05-07 | -5 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/109 | SER | O-05 | 22.91 | 2026-03-23 | Completed | Completed | 2026-05-18 | 5 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/111 | SER | O-10 | 18.61 | 2026-03-25 | Completed | Completed | 2026-05-09 | -6 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/112 | MAT | O-03 | 98.9 | 2026-03-26 | Completed | Completed | 2026-05-31 | 15 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/113 | MAT | O-02 | 553.5 | 2026-03-26 | Completed | Completed | 2026-05-10 | -6 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/114 | MAT | O-03 | 960.73 | 2026-03-27 | Completed | Completed | 2026-06-21 | 35 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/115 | SER | O-09 | 94.38 | 2026-03-28 | Completed | Completed | 2026-05-20 | 2 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/116 | SER | O-09 | 8594.65 | 2026-03-29 | Completed | Completed | 2026-06-15 | 27 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/118 | SER | O-08 | 23.44 | 2026-03-30 | Completed | Completed | 2026-05-15 | -5 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/119 | SER | O-06 | 588.47 | 2026-03-31 | Completed | Completed | 2026-06-14 | 24 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/124 | SER | O-07 | 8420.6 | 2026-04-04 | Completed | Completed | 2026-06-06 | 12 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/127 | MAT | O-03 | 4395.98 | 2026-04-06 | Completed | Completed | 2026-05-23 | -4 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/130 | WRK | O-05 | 851.36 | 2026-04-08 | Completed | Completed | 2026-06-01 | 3 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/131 | SER | O-10 | 635.23 | 2026-04-09 | Completed | Completed | 2026-06-15 | 16 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/132 | SER | O-10 | 532.55 | 2026-04-10 | Completed | Completed | 2026-05-27 | -4 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/134 | WRK | O-08 | 342.95 | 2026-04-11 | Completed | Completed | 2026-06-01 | 0 | On Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/135 | SER | O-08 | 90.32 | 2026-04-12 | Completed | Completed | 2026-05-31 | -2 | Before Timeline | Completed | Order issued and tender closed
IOC/BD/26-27/136 | MAT | O-02 | 91.53 | 2026-04-13 | Completed | Completed | 2026-06-25 | 22 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/141 | SER | O-06 | 63.06 | 2026-04-17 | Completed | Completed | 2026-06-14 | 7 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/142 | SER | O-08 | 6029.5 | 2026-04-17 | Completed | Completed | 2026-06-13 | 6 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/146 | SER | O-07 | 7110.97 | 2026-04-20 | Completed | Completed | 2026-06-26 | 16 | Delayed | Completed | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/148 | MAT | O-01 | 3626.28 | 2026-04-22 | Completed | Completed | 2026-06-14 | 2 | Delayed | Completed | Order issued and tender closed
IOC/BD/26-27/150 | WRK | O-08 | 403.67 | 2026-04-23 | Completed | Completed | 2026-06-21 | 8 | Delayed | Completed | Order issued and tender closed

## Cancelled Tenders
Tender ID | Category | Officer ID | Estimate Value (Lakhs) | File/Tender Received Date | Current Stage | Pending With | Planned Date | Delay Days | SLA Status | Tender Status | Remarks
IOC/BD/26-27/029 | MAT | O-02 | 976.29 | 2026-01-22 | PBO Date | Cancelled |  |  | Cancelled | Cancelled | Tender cancelled as less than 2 bidders remained after evaluation
IOC/BD/26-27/032 | SER | O-06 | 665 | 2026-01-24 | TBA Date | Cancelled |  |  | Cancelled | Cancelled | Tender cancelled due to less than 3 bidders
IOC/BD/26-27/054 | SER | O-07 | 64.89 | 2026-02-10 | Technical Bid Opening Date | Cancelled |  |  | Cancelled | Cancelled | Tender cancelled due to change in PQC after floating
IOC/BD/26-27/060 | SER | O-07 | 52.92 | 2026-02-14 | Workability/Reasonability Date | Cancelled |  |  | Cancelled | Cancelled | Tender cancelled as L1 bidder backed out after PBO
IOC/BD/26-27/091 | SER | O-09 | 364.15 | 2026-03-10 | PBO Date | Cancelled |  |  | Cancelled | Cancelled | Tender cancelled as less than 2 bidders remained after evaluation
IOC/BD/26-27/106 | SER | O-04 | 589.29 | 2026-03-21 | TBA Date | Cancelled |  |  | Cancelled | Cancelled | Tender cancelled due to less than 3 bidders
IOC/BD/26-27/138 | MAT | O-01 | 99.39 | 2026-04-14 | Technical Bid Opening Date | Cancelled |  |  | Cancelled | Cancelled | Tender cancelled due to change in PQC after floating
IOC/BD/26-27/159 | SER | O-04 | 762.29 | 2026-04-30 | Workability/Reasonability Date | Cancelled |  |  | Cancelled | Cancelled | Tender cancelled as L1 bidder backed out after PBO
IOC/BD/26-27/178 | MAT | O-01 | 556.99 | 2026-05-14 | PBO Date | Cancelled |  |  | Cancelled | Cancelled | Tender cancelled as less than 2 bidders remained after evaluation
IOC/BD/26-27/179 | MAT | O-03 | 61.92 | 2026-05-15 | TBA Date | Cancelled |  |  | Cancelled | Cancelled | Tender cancelled due to less than 3 bidders

## Officer Workload
Officer ID | Officer Name | Total_Running_Tenders | Delayed_Tenders | Before_Timeline | On_Timeline
O-01 | Priya Sharma | 9 | 2 | 7 | 0
O-02 | Neha Gupta | 12 | 4 | 8 | 0
O-03 | Rahul Verma | 5 | 3 | 2 | 0
O-04 | Amit Singh | 11 | 6 | 5 | 0
O-05 | Rajesh Kumar | 12 | 3 | 9 | 0
O-06 | Vikas Sharma | 12 | 11 | 1 | 0
O-07 | Sandeep Gupta | 6 | 2 | 4 | 0
O-08 | Manish Verma | 3 | 1 | 2 | 0
O-09 | Arjun Yadav | 8 | 6 | 2 | 0
O-10 | Pooja Agarwal | 12 | 3 | 9 | 0

## Exception Report
Tender ID | Officer ID | Tender Status | Current Stage | Exception Reason | Remarks
IOC/BD/26-27/001 | O-07 | Completed | Completed | Price Comparison Date date is earlier than PBO Date; Order Issued Date date is earlier than Award Approval Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/005 | O-03 | Completed | Completed | Price Comparison Date date is earlier than PBO Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/007 | O-02 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/008 | O-02 | Completed | Completed | PBO Date date is earlier than CBA Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/009 | O-09 | Completed | Completed | PBO Date date is earlier than CBA Date; Order Issued Date date is earlier than Award Approval Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/013 | O-02 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/022 | O-01 | Completed | Completed | Award Approval Date date is earlier than Workability/Reasonability Date | Order issued and tender closed
IOC/BD/26-27/024 | O-02 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/025 | O-05 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/027 | O-01 | Under Process | Workability/Reasonability Date | Price Comparison Date date is earlier than PBO Date | Price reasonability/workability under review
IOC/BD/26-27/030 | O-03 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/034 | O-04 | Completed | Completed | PBO Date date is earlier than CBA Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/036 | O-07 | Completed | Completed | Price Comparison Date date is earlier than PBO Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/042 | O-06 | Completed | Completed | Award Approval Date date is earlier than Workability/Reasonability Date | Order issued and tender closed
IOC/BD/26-27/043 | O-04 | Completed | Completed | Price Comparison Date date is earlier than PBO Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/050 | O-09 | Completed | Completed | Price Comparison Date date is earlier than PBO Date; Order Issued Date date is earlier than Award Approval Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/063 | O-08 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/065 | O-02 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/067 | O-08 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/068 | O-08 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/069 | O-08 | Completed | Completed | PBO Date date is earlier than CBA Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/070 | O-07 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/071 | O-05 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/072 | O-05 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/073 | O-08 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/075 | O-06 | Completed | Completed | Price Comparison Date date is earlier than PBO Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/077 | O-04 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/081 | O-03 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/083 | O-10 | Completed | Completed | Price Comparison Date date is earlier than PBO Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/084 | O-06 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/085 | O-09 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/095 | O-09 | Under Process | Workability/Reasonability Date | PBO Date date is earlier than CBA Date | Award approval under process
IOC/BD/26-27/100 | O-06 | Under Process | Workability/Reasonability Date | Price Comparison Date date is earlier than PBO Date | Price reasonability/workability under review
IOC/BD/26-27/107 | O-01 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/111 | O-10 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/114 | O-03 | Completed | Completed | Price Comparison Date date is earlier than PBO Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/115 | O-09 | Completed | Completed | Award Approval Date date is earlier than Workability/Reasonability Date | Order issued and tender closed
IOC/BD/26-27/118 | O-08 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/119 | O-06 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/121 | O-04 | Under Process | Workability/Reasonability Date | Price Comparison Date date is earlier than PBO Date | Price reasonability/workability under review
IOC/BD/26-27/123 | O-01 | Under Process | Award Approval Date | Price Comparison Date date is earlier than PBO Date | Award approval under process
IOC/BD/26-27/124 | O-07 | Completed | Completed | PBO Date date is earlier than CBA Date; Order Issued Date date is earlier than Award Approval Date | Order issued after SLA due to evaluation/approval delay
IOC/BD/26-27/126 | O-04 | Under Process | Negotiation Date | Price Comparison Date date is earlier than PBO Date | Negotiation in progress; revised offer awaited
IOC/BD/26-27/127 | O-03 | Completed | Completed | Award Approval Date date is earlier than Workability/Reasonability Date | Order issued and tender closed
IOC/BD/26-27/132 | O-10 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/133 | O-03 | Under Process | Workability/Reasonability Date | Price Comparison Date date is earlier than PBO Date | Award approval under process
IOC/BD/26-27/135 | O-08 | Completed | Completed | Order Issued Date date is earlier than Award Approval Date | Order issued and tender closed
IOC/BD/26-27/146 | O-07 | Completed | Completed | Price Comparison Date date is earlier than PBO Date | Order issued after SLA due to evaluation/approval delay